## WBS
PROJECT WORK BREAKDOWN STRUCTURE
STT | Function/Screen | Feature | Vai trò thực hiện | Phụ trách | Level* | Function/Screen Details | Planned | Deadline | Status
1 | Create User Account | Authentication & Account | Admin | Nhi | Medium | Create or initialize a new user account in the system. |  |  | Done
2 | Login | Authentication & Account | Tất cả vai trò | Nhi | Medium | Allow users of all roles to log in to the system. | Iteration 1 | 2026-09-07 | Done
3 | Logout | Authentication & Account | Tất cả vai trò | Nhi | Simple | Allow authenticated users to securely log out of the system. | Iteration 1 | 2026-09-07 | Done
4 | Reset Password | Authentication & Account | Tất cả vai trò | Nhi | Simple | Allow users to request and reset their password. | Iteration 1 | 2026-09-07 | Done
5 | Change Password | Authentication & Account | Tất cả vai trò | Nhi | Simple | Allow users to change their personal password. | Iteration 1 | 2026-09-08 | Doing
6 | Verify Identity via MFA | Authentication & Account | Tất cả vai trò | Nhi | Simple | Enable and verify multi-factor authentication for user accounts. | Iteration 1 | 2026-09-09 | Doing
7 | Lock and Unlock User Account | Authentication & Account | Admin | Nhi | Simple | Allow administrators to lock and unlock a user account.
8 | View Login History | Authentication & Account | Admin, Security Officer | Nhi | Medium | Allow authorized users to view account login history.
9 | View User | User Management & Authorization | Admin | Nhi | Simple
10 | Add User | User Management & Authorization | Admin | Nhi | Medium | Create a new user and add the user to the system.
11 | Edit User | User Management & Authorization | Admin | Nhi | Medium | Update user profile and account information.
12 | Deactivate User | User Management & Authorization | Admin | Nhi | Medium | Deactivate or remove a user from the system.
13 | Assign User Role | User Management & Authorization | Admin | Nhi | Medium | Assign one or more roles to a user.
14 | Configure Detailed Permissions | User Management & Authorization | Admin | Nhi | Complex | Configure detailed permissions for each module and role.
15 | View Users by Department | User Management & Authorization | Admin | Nhi | Complex | View and filter users based on their department.
16 | Import Users from Excel | User Management & Authorization | Admin | Nhi | Simple | Import multiple user accounts from an Excel file.
17 | Create Custom Role | Role Management | Admin | Hoài | Simple | Create a custom role based on organizational requirements. | Iteration 1 |  | Done
18 | View List Custom Role | Role Management | Admin | Hoài | Simple |  | Iteration 1 |  | Done
19 | View Detail Custom Role | Role Management | Admin | Hoài | Simple |  | Iteration 1 |  | Pending
20 | Update Custom Role | Role Management | Admin | Hoài | Simple |  | Iteration 1 |  | Done
21 | Delete Custom Role | Role Management | Admin | Hoài | Simple |  | Iteration 1 |  | Done
22 | View Asset Detail | IT Asset Management | Security Officer | Dương | Simple | View the detail of IT assets managed by the organization. | Iteration 1 |  | Done
23 | Create IT Asset | IT Asset Management | Security Officer | Dương | Medium | Add a new IT asset to the system. | Iteration 1 |  | Done
24 | Edit IT Asset | IT Asset Management | Security Officer | Dương | Medium | Update information of an existing IT asset. | Iteration 1 |  | Done
25 | Delete Tracking Asset | IT Asset Management | Security Officer | Dương | Medium | Delete an asset or mark it as no longer being tracked. | Iteration 1 |  | Done
26 | View Asset List | IT Asset Management | Security Officer, Employee, Executive | Dương | Simple | View the list of IT assets managed by the organization. | Iteration 1 |  | Done
27 | Search and Filter Assets | IT Asset Management | Security Officer | Dương | Simple | Search and filter assets based on selected criteria. | Iteration 1 |  | Done
28 | Classify Asset Criticality | IT Asset Management | Security Officer | Dương | Medium | Classify assets based on their level of importance or criticality. | Iteration 1 |  | Done
29 | Assign Asset Owner | IT Asset Management | Security Officer | Dương | Medium | Assign a responsible owner to each IT asset. | Iteration 1 |  | Done
30 | Import Assets from Excel | IT Asset Management | Security Officer | Dương | Medium | Import multiple IT assets from an Excel file. | Iteration 1 |  | Done
31 | Export Asset List | IT Asset Management | Security Officer, Executive | Dương | Medium | Export the IT asset list to a file. | Iteration 1 |  | Done
32 | View Asset Change History | IT Asset Management | Security Officer, Admin | Dương | Medium | View the history of changes made to asset information. | Iteration 1 |  | Done
33 | Create Risk Assessment | Risk Assessment | Security Officer | Dương | Medium | Create a risk assessment for an IT asset or business process. | Iteration 1
| View Risk Assessment | Risk Assessment | Security Officer | Dương | Simple | View a list of risk assessments. | Iteration 1
| View Risk Assessment Detail | Risk Assessment | Security Officer | Dương | Simple | View detailed information of a selected risk assessment. | Iteration 1
| Edit Risk Assessment | Risk Assessment | Security Officer | Dương | Medium | Update the information of an existing risk assessment. | Iteration 1
| Cancel Risk Assessment | Risk Assessment | Security Officer | Dương | Medium | Cancel an existing risk assessment that is no longer needed or was created incorrectly. | Iteration 1
34 | Identify Threat | Risk Assessment | Security Officer | Dương | Medium | Identify threats related to the assessed asset or process.
35 | Identify Vulnerability | Risk Assessment | Security Officer | Dương | Medium | Identify vulnerabilities related to the assessed asset or process.
36 | Automatically Calculate Risk Score | Risk Assessment | Security Officer | Dương | Medium | Automatically calculate risk scores based on likelihood and impact.
37 | Suggest Risk Treatment Measures | Risk Assessment | Security Officer | Dương | Medium | Provide suggested measures for handling identified risks.
38 | Submit Risk Treatment Plan for Approval | Risk Assessment | Security Officer | Dương | Medium | Send a risk treatment plan to the approval workflow.
39 | Approve Risk Treatment Plan | Risk Assessment | Executive | Dương | Medium | Allow management to approve a submitted risk treatment plan.
40 | Reject and Request Risk Assessment Revision | Risk Assessment | Executive | Dương | Medium | Reject a risk assessment or request revisions before approval.
41 | Track Risk Treatment Progress | Risk Assessment | Security Officer, Executive | Dương | Medium | Monitor the progress of risk treatment activities.
42 | Close Resolved Risk | Risk Assessment | Security Officer | Dương | Medium | Close a risk after the planned treatment has been completed.
43 | View Risk Heat Map | Risk Assessment | Security Officer, Executive | Dương | Medium | Display a visual risk heat map based on risk levels.
44 | Compare Risk Changes Between Assessment Periods | Risk Assessment | Executive | Dương | Medium | Compare changes in risk levels across different assessment periods.
45 | Draft Information Security Policy | Policy & Compliance Control | Security Officer | Khoa | Medium | Create and draft an information security policy. |  |  | Done
46 | Publish Official Policy Version | Policy & Compliance Control | Admin | Khoa | Medium | Publish an official version of an approved policy. |  |  | Done
47 | Update Policy and Create New Version | Policy & Compliance Control | Security Officer | Khoa | Medium | Update an existing policy and create a new version. |  |  | Done
48 | Assign Policy to Department | Policy & Compliance Control | Security Officer | Khoa | Medium | Assign applicable policies to specific departments or units. |  |  | Done
49 | Confirm Policy Reading and Understanding | Policy & Compliance Control | Employee | Khoa | Medium | Allow employees to confirm that they have read and understood a policy. |  |  | Done
50 | Map Controls to Standard Framework | Policy & Compliance Control | Security Officer | Khoa | Medium | Map security controls to ISO 27001 or NIST frameworks. |  |  | Doing
51 | Assess Control Compliance | Policy & Compliance Control | Security Officer | Khoa | Medium | Assess the compliance level of individual security controls.
52 | Upload Compliance Evidence | Policy & Compliance Control | Security Officer, Employee | Khoa | Medium | Upload documents or other evidence supporting compliance.
53 | View Policy Version History | Policy & Compliance Control | Tất cả vai trò | Khoa | Simple | View the history of all policy versions.
54 | Receive Compliance Reminders | Policy & Compliance Control | Employee, Security Officer | Khoa | Simple | Automatically send reminders for compliance-related deadlines.
55 | Report New Incident | Information Security Incident Management | Employee, Security Officer | Khoa | Medium | Record or submit a new information security incident.
56 | Classify Incident Severity | Information Security Incident Management | Security Officer | Khoa | Medium | Classify the severity level of a reported incident.
57 | Assign Incident Handler | Information Security Incident Management | Security Officer | Khoa | Medium | Assign a person or team responsible for handling an incident.
58 | Update Incident Handling Progress | Information Security Incident Management | Security Officer | Khoa | Medium | Update the current progress and status of incident handling.
59 | Attach Incident Evidence and Logs | Information Security Incident Management | Security Officer | Khoa | Medium | Attach evidence and related log files to an incident.
60 | Escalate Critical Incident | Information Security Incident Management | Security Officer | Khoa | Medium | Escalate a serious incident to management.
61 | Close Resolved Incident | Information Security Incident Management | Security Officer | Khoa | Medium | Close an incident after the handling process is completed.
62 | Create Post-Incident Report | Information Security Incident Management | Security Officer | Khoa | Medium | Create a report summarizing the incident and its resolution.
63 | View Incident History | Information Security Incident Management | Security Officer, Executive | Khoa | Medium | View the history of previously handled incidents.
64 | Link Incident to Related Risk | Information Security Incident Management | Security Officer | Khoa | Medium | Link an incident with a previously identified or assessed risk.
65 | Configure Log and Data Source | AI Anomaly Detection & Alerts | Admin, Security Officer | Hoài | Medium | Configure log and data sources for AI analysis. | Iteration 1 | 2026-09-08 | Done
66 | Configure Anomaly Detection Rules and Thresholds | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Fine-tune the anomaly detection model based on organizational behavior. | Iteration 1 | 2026-09-10 | Done
67 | View Real-Time AI Alerts | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | View the list of AI-generated alerts in real time. | Iteration 1 |  | Done
68 | Evaluate Alert Reliability | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Provide feedback on the reliability of AI-generated alerts. | Iteration 1 |  | Done
69 | Confirm AI Alert as Real Incident | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Confirm that an AI-generated alert represents a real security incident. | Iteration 1 |  | Done
70 | Mark False Positive | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Mark an incorrect AI alert as a false positive for model improvement. | Iteration 2 |  | Done
71 | View AI-Suggested Risk Level | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | View the risk level suggested by the AI system. | Iteration 2 |  | Done
72 | View Explainable AI Decision | AI Anomaly Detection & Alerts | Security Officer, Executive | Hoài | Medium | View the explanation of factors influencing the AI decision. | Iteration 2 |  | Done
73 | Automatically Create Incident Draft | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Automatically generate a draft incident record from an AI alert. | Iteration 2 |  | Done
74 | Set Custom Alert Threshold | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Set customized alert thresholds for individual assets. | Iteration 2 |  | Done
75 | Create Security Awareness Course | Security Awareness Training | Security Officer | Hoài | Medium | Create a security awareness training course or content. | Iteration 2 |  | Done
76 | Assign Training Course | Security Awareness Training | Security Officer | Hoài | Medium | Assign a training course to employees or departments.
77 | Take Post-Training Assessment | Security Awareness Training | Employee | Hoài | Medium | Allow employees to take an assessment after completing training.
78 | Track Training Completion | Security Awareness Training | Security Officer, Executive | Hoài | Medium | Monitor training completion progress. | Iteration 3
79 | Send Training Deadline Reminder | Security Awareness Training | Employee | Hoài | Medium | Send reminders for incomplete training approaching its deadline. | Iteration 3
80 | Issue Training Completion Certificate | Security Awareness Training | Security Officer | Hoài | Medium | Issue a certificate after successful completion of training. | Iteration 3
81 | View Department Training Completion Report | Security Awareness Training | Executive | Hoài | Medium | View training completion rates by department. | Iteration 3
82 | View Real-Time Risk and Incident Dashboard | Reports & Dashboard | Tất cả vai trò | Thịnh | Medium | Display an overview dashboard of risks and incidents in real time. | Iteration 3
83 | Export Periodic Risk Report | Reports & Dashboard | Security Officer | Thịnh | Medium | Export periodic risk reports in PDF or Excel format. | Iteration 3
84 | Export Compliance Report | Reports & Dashboard | Security Officer | Thịnh | Medium | Export compliance reports based on selected standard frameworks. | Iteration 3
85 | Customize Dashboard Widgets | Reports & Dashboard | Tất cả vai trò | Thịnh | Medium | Allow users to customize dashboard widgets based on their role. | Iteration 3
86 | Compare Security Metrics Between Reporting Periods | Reports & Dashboard | Executive | Thịnh | Medium | Compare information security metrics across reporting periods. | Iteration 3
87 | Create Information Security KPI Report | Reports & Dashboard | Security Officer | Thịnh | Medium | Create a report containing information security KPIs. | Iteration 3
88 | View Executive Summary Report | Reports & Dashboard | Executive | Thịnh | Medium | View a summarized report designed for management. | Iteration 3
89 | Schedule Automatic Email Reports | Reports & Dashboard | Security Officer, Admin | Thịnh | Medium | Schedule reports to be automatically sent via email. | Iteration 3
90 | Send In-System Notification | Notification & System Logs | Admin | Nhi | Medium | Send notifications to users within the system.
91 | Send Email Notification | Notification & System Logs | Admin | Nhi | Simple | Send notifications to users via email.
92 | Configure Personal Notification Channel | Notification & System Logs | Tất cả vai trò | Nhi | Medium | Allow users to configure their preferred notification channels.
93 | View User Activity Audit Log | Notification & System Logs | Admin | Nhi | Medium | View logs of user activities performed in the system.
94 | Search Logs with Advanced Filters | Notification & System Logs | Admin, Security Officer | Nhi | Medium | Search and filter system logs using advanced criteria.
95 | Export Investigation Logs | Notification & System Logs | Admin | Nhi | Medium | Export logs for security investigation purposes.
96 | View System Configuration Change History | Notification & System Logs | Admin | Nhi | Medium | View the history of changes to system configurations.
97 | Configure Custom Approval Workflow | Approval & Workflow | Admin | Thịnh | Medium | Create and configure customized approval workflows. | Iteration 2
98 | Approve and Reject Request | Approval & Workflow | Executive, Security Officer | Thịnh | Medium | Allow authorized users to approve and reject system requests. | Iteration 2
99 | Delegate Temporary Approval Authority | Approval & Workflow | Executive | Thịnh | Medium | Allow temporary delegation of approval authority when unavailable. | Iteration 2
100 | Track Pending Request Status | Approval & Workflow | Tất cả vai trò | Thịnh | Medium | View and track the status of requests awaiting processing. | Iteration 2 |  | Pending
101 | Receive Overdue Approval Reminder | Approval & Workflow | Executive | Thịnh | Medium | Send reminders when approval requests exceed their deadlines. | Iteration 2
102 | View Approval Decision History | Approval & Workflow | Admin, Executive | Thịnh | Medium | View the history of approval and rejection decisions. | Iteration 2
103 | Create Integration SIEM / Firewall | Integration & API | Admin | Thịnh | Medium | Modal/form to configure a new external SIEM, Firewall, or API endpoint with Base URL, integration type, and custom JSON settings. | Iteration 1 |  | Done
104 | Test Connection / Ping Handshake | Integration & API | Admin | Thịnh | Medium | Dialog/action to send a live probe to the external endpoint and display latency (ms), HTTP status code, and reachability. | Iteration 1 |  | Done
105 | List & Monitor Integrations Overview | Integration & API | Admin | Thịnh | Medium | Main dashboard view displaying connected SIEM/Firewall systems with status badges, type filters, and health summaries. | Iteration 1 |  | Done
106 | View Integration Details | Integration & API | Admin | Thịnh | Medium | Drawer/detail view showing full integration properties, connected log sources, sync schedules, API keys, and activity logs. | Iteration 1 |  | Done
107 | Update Integration Settings | Integration & API | Admin | Thịnh | Medium | Modal/form to modify integration metadata, Base URL, port, and custom JSON configurations with audit tracking. | Iteration 1 |  | Done
108 | Enable / Disable Integration | Integration & API | Admin | Thịnh | Medium | Action to toggle integration status between Active and Inactive without losing historical sync data. | Iteration 1 |  | Done
109 | Delete Integration | Integration & API | Admin | Thịnh | Medium | Confirmation dialog to permanently remove an unused integration and handle dependent configurations. | Iteration 1 |  | Done
110 | Create Sync Schedule | Integration & API | Admin | Thịnh | Medium | Modal to define automated log synchronization frequency using visual presets or custom Cron expressions. | Iteration 1 |  | Done
111 | View List Sync Schedules | Integration & API | Admin | Thịnh | Medium | Tab view listing all recurring sync schedules with humanized descriptions, active statuses, and next run timestamps. | Iteration 1 |  | Done
112 | Update Sync Schedule | Integration & API | Admin | Thịnh | Medium | Modal/form to edit Cron expressions and automatically recalculate next execution dates for existing schedules. | Iteration 1 |  | Done
113 | Resume / Pause Schedule | Integration & API | Admin | Thịnh | Medium | Action to toggle schedule state between Active and Paused without deleting the schedule entry. | Iteration 1 |  | Done
114 | Delete Sync Schedule | Integration & API | Admin | Thịnh | Medium | Confirmation modal to safely delete an unnecessary log synchronization schedule. | Iteration 1 |  | Done
115 | Trigger Manual Sync Now | Integration & API | Admin | Thịnh | Medium | Action button to immediately execute an ad-hoc log synchronization job outside regular schedules. | Iteration 1 |  | Done
116 | View Sync Jobs / History | Integration & API | Admin | Thịnh | Medium | Table view displaying historical sync job executions, completion statuses, processed/failed record counts, and duration. | Iteration 1 |  | Done
117 | View Integration API Key List | Integration & API | Admin | Thịnh | Medium | Table view displaying API key names, fingerprints, computed statuses (Active/Expired/Inactive), and expiration dates. | Iteration 1 |  | Done
118 | View Integration API Key Detail | Integration & API | Admin | Thịnh | Medium | Panel/modal displaying metadata, fingerprint, expiration date, and operational status of a specific API key. | Iteration 1 |  | Done
119 | Create Integration API Key | Integration & API | Admin | Thịnh | Medium | Modal with CSPRNG token generator and a Show-Once Secret Dialog to issue encrypted AES-256-GCM API credentials. | Iteration 1 |  | Done
120 | Update Integration API Key Metadata | Integration & API | Admin | Thịnh | Medium | Modal/form to update the display name and expiration date of an existing API key without altering secret tokens. | Iteration 1 |  | Done
121 | Rotate Integration API Key | Integration & API | Admin | Thịnh | Medium | Modal to safely roll over an API key with a newly generated secret token and one-time secret revelation. | Iteration 1 |  | Done
122 | Deactivate / Revoke Integration API Key | Integration & API | Admin | Thịnh | Medium | Confirmation dialog to immediately revoke an API key and prevent further external authentication. | Iteration 1 |  | Done
123 | Reactivate Integration API Key | Integration & API | Admin | Thịnh | Medium | Action to re-enable a previously deactivated API key when still within its validity period. | Iteration 1 |  | Done
124 | Search and Filter Integration API Keys | Integration & API | Admin | Thịnh | Medium | Toolbar to search keys by name and filter by lifecycle status (All, Active, Inactive). | Iteration 1 |  | Done
125 | View Fleet-wide Connection Metrics | Integration & API | Admin | Thịnh | Medium | Displays a consolidated KPI metric strip summarizing the health and availability of all configured external integrations. | Iteration 1 |  | Doing
126 | View Live Connection Status Table | Integration & API | Admin | Thịnh | Medium | Presents a detailed operational data table for monitoring third-party SIEM and Firewall connections in real time. | Iteration 1 |  | Doing
127 | Check Active Connection Probing | Integration & API | Admin | Thịnh | Medium | Allows administrators to trigger manual on-demand diagnostic checks to verify connectivity without waiting for scheduled cycles. | Iteration 1 |  | Doing
128 | Diagnostic Telemetry & Timeline | Integration & API | Admin | Thịnh | Medium | Provides an in-depth diagnostic drawer for a selected integration, highlighting 24-hour reliability metrics and historical connection check logs. | Iteration 1 |  | Doing
129 | Auto-refresh Polling | Integration & API | Admin | Thịnh | Medium | Enables configurable client-side polling intervals to maintain up-to-date connection telemetry during live monitoring sessions. | Iteration 1 |  | Doing
130 | View List Sync Error Logs | Integration & API | Admin | Thịnh | Medium | Table view displaying synchronization log events with timestamps, severity levels, and summary error messages. | Iteration 1 |  | Done
131 | Filter & Search Logs | Integration & API | Admin | Thịnh | Medium | Toolbar to filter log entries by severity level (Error, Warn, Info), date range, and search keywords. | Iteration 1 |  | Done
132 | View Error Details & Payload | Integration & API | Admin | Thịnh | Medium | Modal displaying detailed JSON error payload, HTTP status codes, network stack trace, and copyable diagnostics. | Iteration 1 |  | Done
133 | Sync Failure Analytics / Metrics | Integration & API | Admin | Thịnh | Medium | Metric strip showing sync success/failure rates and total failed records across synchronization jobs. | Iteration 1 |  | Done
134 | Retry Sync after Failure | Integration & API | Admin | Thịnh | Medium | Action button to re-trigger a failed synchronization job immediately after resolving network or credential issues. | Iteration 1 |  | Done
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple | <=7 fields |  |  | <=3 transactions
| medium | <=15 fields |  |  | <= 7 transactions
| complex | >15 fields |  |  | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 |  |  | Medium | HuyNMG |  |  | Open
2 |  |  | Medium | HuyNMG |  |  | Open
3 |  |  | Medium | HuyNG |  |  | Open
4 |  |  | Medium | HuyNG |  |  | Open
5 |  |  | Medium | HuyNG |  |  | Open
6 |  |  | Medium | DucBH |  |  | Open
7 |  |  | Medium | HuyLQ |  |  | Open

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open

## Testing
Này bảng nháp của Thịnh đừng xó 😉
PROJECT WORK BREAKDOWN STRUCTURE
STT | Function/Screen | Feature | Vai trò thực hiện | SV5 | Status | Level* | Function/Screen Details | Phụ trách
1 | Authentication & Account | Initialize User Account | Admin | Testing | Pending | Medium | Create or initialize a new user account in the system. | Nhi
2 | Authentication & Account | Login | Tất cả vai trò | Testing |  | Medium | Allow users of all roles to log in to the system. | Nhi
3 | Authentication & Account | Logout | Tất cả vai trò | Testing |  | Simple | Allow authenticated users to securely log out of the system. | Nhi
4 | Authentication & Account | Reset Password | Tất cả vai trò | Testing |  | Simple | Allow users to request and reset their password. | Nhi
5 | Authentication & Account | Change Password | Tất cả vai trò | Testing |  | Simple | Allow users to change their personal password. | Nhi
6 | Authentication & Account | Verify Identity via MFA | Tất cả vai trò | Testing |  | Simple | Enable and verify multi-factor authentication for user accounts. | Nhi
7 | Authentication & Account | Lock and Unlock User Account | Admin | Testing |  | Simple | Allow administrators to lock and unlock a user account. | Nhi
8 | Authentication & Account | View Login History | Admin, Security Officer | Testing |  | Medium | Allow authorized users to view account login history. | Nhi
9 | User Management & Authorization | Add User | Admin | Testing |  | Medium | Create a new user and add the user to the system. | Nhi
10 | User Management & Authorization | Edit User Information | Admin | Testing |  | Medium | Update user profile and account information. | Nhi
11 | User Management & Authorization | Deactivate User | Admin | Testing |  | Medium | Deactivate or remove a user from the system. | Nhi
12 | User Management & Authorization | Assign User Role | Admin | Testing |  | Medium | Assign one or more roles to a user. | Nhi
13 | User Management & Authorization | Create Custom Role | Admin | Testing |  | Medium | Create a custom role based on organizational requirements. | Nhi
14 | User Management & Authorization | Configure Detailed Permissions | Admin | Testing |  | Complex | Configure detailed permissions for each module and role. | Nhi
15 | User Management & Authorization | View Users by Department | Admin | Testing |  | Complex | View and filter users based on their department. | Nhi
16 | User Management & Authorization | Import Users from Excel | Admin | Testing |  | Simple | Import multiple user accounts from an Excel file. | Nhi
17 | IT Asset Management | Add IT Asset | Security Officer | Testing |  | Medium | Add a new IT asset to the system. | Dương
18 | IT Asset Management | Edit IT Asset | Security Officer | Testing |  | Medium | Update information of an existing IT asset. | Dương
19 | IT Asset Management | Delete Tracking Asset | Security Officer | Testing |  | Medium | Delete an asset or mark it as no longer being tracked. | Dương
20 | IT Asset Management | View Asset List | Security Officer, Employee, Executive | Testing |  | Simple | View the list of IT assets managed by the organization. | Dương
21 | IT Asset Management | Search and Filter Assets | Security Officer | Testing |  | Medium | Search and filter assets based on selected criteria. | Dương
22 | IT Asset Management | Classify Asset Criticality | Security Officer | Testing |  | Medium | Classify assets based on their level of importance or criticality. | Dương
23 | IT Asset Management | Assign Asset Owner | Security Officer | Testing |  | Medium | Assign a responsible owner to each IT asset. | Dương
24 | IT Asset Management | Import Assets from Excel | Security Officer | Testing |  | Medium | Import multiple IT assets from an Excel file. | Dương
25 | IT Asset Management | Export Asset List | Security Officer, Executive | Testing |  | Medium | Export the IT asset list to a file. | Dương
26 | IT Asset Management | View Asset Change History | Security Officer, Admin | Testing |  | Medium | View the history of changes made to asset information. | Dương
27 | Risk Assessment | Create Risk Assessment | Security Officer | Testing + integration với Workflow |  | Medium | Create a risk assessment for an IT asset or business process. | Dương
28 | Risk Assessment | Identify Threat | Security Officer | Testing + integration với Workflow |  | Medium | Identify threats related to the assessed asset or process. | Dương
29 | Risk Assessment | Identify Vulnerability | Security Officer | Testing + integration với Workflow |  | Medium | Identify vulnerabilities related to the assessed asset or process. | Dương
30 | Risk Assessment | Automatically Calculate Risk Score | Security Officer | Testing + integration với Workflow |  | Medium | Automatically calculate risk scores based on likelihood and impact. | Dương
31 | Risk Assessment | Suggest Risk Treatment Measures | Security Officer | Testing + integration với Workflow |  | Medium | Provide suggested measures for handling identified risks. | Dương
32 | Risk Assessment | Submit Risk Treatment Plan for Approval | Security Officer | Testing + integration với Workflow |  | Medium | Send a risk treatment plan to the approval workflow. | Dương
33 | Risk Assessment | Approve Risk Treatment Plan | Executive | Testing + integration với Workflow |  | Medium | Allow management to approve a submitted risk treatment plan. | Dương
34 | Risk Assessment | Reject and Request Risk Assessment Revision | Executive | Testing + integration với Workflow |  | Medium | Reject a risk assessment or request revisions before approval. | Dương
35 | Risk Assessment | Track Risk Treatment Progress | Security Officer, Executive | Testing + integration với Workflow |  | Medium | Monitor the progress of risk treatment activities. | Dương
36 | Risk Assessment | Close Resolved Risk | Security Officer | Testing + integration với Workflow |  | Medium | Close a risk after the planned treatment has been completed. | Dương
37 | Risk Assessment | View Risk Heat Map | Security Officer, Executive | Testing + integration với Workflow |  | Medium | Display a visual risk heat map based on risk levels. | Dương
38 | Risk Assessment | Compare Risk Changes Between Assessment Periods | Executive | Testing + integration với Workflow |  | Medium | Compare changes in risk levels across different assessment periods. | Dương
39 | Policy & Compliance Control | Draft Information Security Policy | Security Officer | Testing + integration với Workflow |  | Medium | Create and draft an information security policy. | Khoa
40 | Policy & Compliance Control | Publish Official Policy Version | Admin | Testing + integration với Workflow |  | Medium | Publish an official version of an approved policy. | Khoa
41 | Policy & Compliance Control | Update Policy and Create New Version | Security Officer | Testing + integration với Workflow |  | Medium | Update an existing policy and create a new version. | Khoa
42 | Policy & Compliance Control | Assign Policy to Department | Security Officer | Testing + integration với Workflow |  | Medium | Assign applicable policies to specific departments or units. | Khoa
43 | Policy & Compliance Control | Confirm Policy Reading and Understanding | Employee | Testing + integration với Workflow |  | Medium | Allow employees to confirm that they have read and understood a policy. | Khoa
44 | Policy & Compliance Control | Map Controls to Standard Framework | Security Officer | Testing + integration với Workflow |  | Medium | Map security controls to ISO 27001 or NIST frameworks. | Khoa
45 | Policy & Compliance Control | Assess Control Compliance | Security Officer | Testing + integration với Workflow |  | Medium | Assess the compliance level of individual security controls. | Khoa
46 | Policy & Compliance Control | Upload Compliance Evidence | Security Officer, Employee | Testing + integration với Workflow |  | Medium | Upload documents or other evidence supporting compliance. | Khoa
47 | Policy & Compliance Control | View Policy Version History | Tất cả vai trò | Testing + integration với Workflow |  | Simple | View the history of all policy versions. | Khoa
48 | Policy & Compliance Control | Receive Compliance Reminders | Employee, Security Officer | Testing + integration với Workflow |  | Simple | Automatically send reminders for compliance-related deadlines. | Khoa
49 | Information Security Incident Management | Report New Incident | Employee, Security Officer | Testing |  | Medium | Record or submit a new information security incident. | Khoa
50 | Information Security Incident Management | Classify Incident Severity | Security Officer | Testing |  | Medium | Classify the severity level of a reported incident. | Khoa
51 | Information Security Incident Management | Assign Incident Handler | Security Officer | Testing |  | Medium | Assign a person or team responsible for handling an incident. | Khoa
52 | Information Security Incident Management | Update Incident Handling Progress | Security Officer | Testing |  | Medium | Update the current progress and status of incident handling. | Khoa
53 | Information Security Incident Management | Attach Incident Evidence and Logs | Security Officer | Testing |  | Medium | Attach evidence and related log files to an incident. | Khoa
54 | Information Security Incident Management | Escalate Critical Incident | Security Officer | Testing |  | Medium | Escalate a serious incident to management. | Khoa
55 | Information Security Incident Management | Close Resolved Incident | Security Officer | Testing |  | Medium | Close an incident after the handling process is completed. | Khoa
56 | Information Security Incident Management | Create Post-Incident Report | Security Officer | Testing |  | Medium | Create a report summarizing the incident and its resolution. | Khoa
57 | Information Security Incident Management | View Incident History | Security Officer, Executive | Testing |  | Medium | View the history of previously handled incidents. | Khoa
58 | Information Security Incident Management | Link Incident to Related Risk | Security Officer | Testing |  | Medium | Link an incident with a previously identified or assessed risk. | Khoa
59 | AI Anomaly Detection & Alerts | Configure Log and Data Source | Admin, Security Officer | Testing |  | Complex | Configure log and data sources for AI analysis. | Hoài
60 | AI Anomaly Detection & Alerts | Fine-Tune Anomaly Detection Model | Security Officer | Testing |  | Complex | Fine-tune the anomaly detection model based on organizational behavior. | Hoài
61 | AI Anomaly Detection & Alerts | View Real-Time AI Alerts | Security Officer | Testing |  | Complex | View the list of AI-generated alerts in real time. | Hoài
62 | AI Anomaly Detection & Alerts | Evaluate Alert Reliability | Security Officer | Testing |  | Medium | Provide feedback on the reliability of AI-generated alerts. | Hoài
63 | AI Anomaly Detection & Alerts | Confirm AI Alert as Real Incident | Security Officer | Testing |  | Medium | Confirm that an AI-generated alert represents a real security incident. | Hoài
64 | AI Anomaly Detection & Alerts | Mark False Positive | Security Officer | Testing |  | Medium | Mark an incorrect AI alert as a false positive for model improvement. | Hoài
65 | AI Anomaly Detection & Alerts | View AI-Suggested Risk Level | Security Officer | Testing |  | Medium | View the risk level suggested by the AI system. | Hoài
66 | AI Anomaly Detection & Alerts | View Explainable AI Decision | Security Officer, Executive | Testing |  | Complex | View the explanation of factors influencing the AI decision. | Hoài
67 | AI Anomaly Detection & Alerts | Automatically Create Incident Draft | Security Officer | Testing |  | Complex | Automatically generate a draft incident record from an AI alert. | Hoài
68 | AI Anomaly Detection & Alerts | Set Custom Alert Threshold | Security Officer | Testing |  | Medium | Set customized alert thresholds for individual assets. | Hoài
69 | Security Awareness Training | Create Security Awareness Course | Security Officer | Testing |  | Medium | Create a security awareness training course or content. | Khoa
70 | Security Awareness Training | Assign Training Course | Security Officer | Testing |  | Medium | Assign a training course to employees or departments. | Khoa
71 | Security Awareness Training | Take Post-Training Assessment | Employee | Testing |  | Medium | Allow employees to take an assessment after completing training. | Khoa
72 | Security Awareness Training | Track Training Completion | Security Officer, Executive | Testing |  | Medium | Monitor training completion progress. | Khoa
73 | Security Awareness Training | Send Training Deadline Reminder | Employee | Testing |  | Medium | Send reminders for incomplete training approaching its deadline. | Khoa
74 | Security Awareness Training | Issue Training Completion Certificate | Security Officer | Testing |  | Medium | Issue a certificate after successful completion of training. | Khoa
75 | Security Awareness Training | View Department Training Completion Report | Executive | Testing |  | Medium | View training completion rates by department. | Khoa
97 | Integration & API | Connect Third-Party SIEM and Firewall API | Admin | Iteration 1 | Doing | Medium | Connect the system with third-party SIEM and firewall APIs. | Thịnh
98 | Integration & API | Schedule Automatic Log Synchronization | Admin | Iteration 1 | Doing | Medium | Automatically synchronize log data based on a configured schedule. | Thịnh
99 | Integration & API | Manage Integration API Keys | Admin | Iteration 1 | Doing | Medium | Create, manage, and revoke API keys used for integrations. | Thịnh
100 | Integration & API | Monitor Integration Connection Status | Admin | Iteration 1 | Doing | Medium | Monitor the current connection status of integrated systems. | Thịnh
101 | Integration & API | View Data Synchronization Error Logs | Admin | Iteration 1 | Doing | Medium | View error logs generated during data synchronization processes. | Thịnh
91 | Approval & Workflow | Configure Custom Approval Workflow | Admin | Iteration 2 | Pending | Medium | Create and configure customized approval workflows. | Thịnh
92 | Approval & Workflow | Approve and Reject Request | Executive, Security Officer | Iteration 2 | Pending | Medium | Allow authorized users to approve and reject system requests. | Thịnh
93 | Approval & Workflow | Delegate Temporary Approval Authority | Executive | Iteration 2 | Pending | Medium | Allow temporary delegation of approval authority when unavailable. | Thịnh
94 | Approval & Workflow | Track Pending Request Status | Tất cả vai trò | Iteration 2 | Pending | Medium | View and track the status of requests awaiting processing. | Thịnh
95 | Approval & Workflow | Receive Overdue Approval Reminder | Executive | Iteration 2 | Pending | Medium | Send reminders when approval requests exceed their deadlines. | Thịnh
96 | Approval & Workflow | View Approval Decision History | Admin, Executive | Iteration 2 | Pending | Medium | View the history of approval and rejection decisions. | Thịnh
76 | Reports & Dashboard | View Real-Time Risk and Incident Dashboard | Tất cả vai trò | Iteration 3 | Pending | Medium | Display an overview dashboard of risks and incidents in real time. | Thịnh
77 | Reports & Dashboard | Export Periodic Risk Report | Security Officer | Iteration 3 | Pending | Medium | Export periodic risk reports in PDF or Excel format. | Thịnh
78 | Reports & Dashboard | Export Compliance Report | Security Officer | Iteration 3 | Pending | Medium | Export compliance reports based on selected standard frameworks. | Thịnh
79 | Reports & Dashboard | Customize Dashboard Widgets | Tất cả vai trò | Iteration 3 | Pending | Medium | Allow users to customize dashboard widgets based on their role. | Thịnh
80 | Reports & Dashboard | Compare Security Metrics Between Reporting Periods | Executive | Iteration 3 | Pending | Medium | Compare information security metrics across reporting periods. | Thịnh
81 | Reports & Dashboard | Create Information Security KPI Report | Security Officer | Iteration 3 | Pending | Medium | Create a report containing information security KPIs. | Thịnh
82 | Reports & Dashboard | View Executive Summary Report | Executive | Iteration 3 | Pending | Medium | View a summarized report designed for management. | Thịnh
83 | Reports & Dashboard | Schedule Automatic Email Reports | Security Officer, Admin | Iteration 3 | Pending | Medium | Schedule reports to be automatically sent via email. | Thịnh
84 | Notification & System Logs | Send In-System Notification | Admin | Testing |  | Medium | Send notifications to users within the system. | Nhi
85 | Notification & System Logs | Send Email Notification | Admin | Testing |  | Simple | Send notifications to users via email. | Nhi
86 | Notification & System Logs | Configure Personal Notification Channel | Tất cả vai trò | Testing |  | Medium | Allow users to configure their preferred notification channels. | Nhi
87 | Notification & System Logs | View User Activity Audit Log | Admin | Testing |  | Medium | View logs of user activities performed in the system. | Nhi
88 | Notification & System Logs | Search Logs with Advanced Filters | Admin, Security Officer | Testing |  | Medium | Search and filter system logs using advanced criteria. | Nhi
89 | Notification & System Logs | Export Investigation Logs | Admin | Testing |  | Medium | Export logs for security investigation purposes. | Nhi
90 | Notification & System Logs | View System Configuration Change History | Admin | Testing |  | Medium | View the history of changes to system configurations. | Nhi
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple | <=7 fields |  |  |  | <=3 transactions
| medium | <=15 fields |  |  |  | <= 7 transactions
| complex | >15 fields |  |  |  | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions