## WBS
PROJECT WORK BREAKDOWN STRUCTURE
STT | Function/Screen | Feature | Role | Owner | Level* | Function/Screen Details | Planned | Status
1 | Login | Authentication & Account | All roles | Nhi | Medium | Allow users of all roles to authenticate using their registered credentials. The system validates the credentials and grants access according to the user's assigned roles and permissions. | Iteration 1 | Done
2 | Logout | Authentication & Account | All roles | Nhi | Simple | Allow authenticated users to securely terminate their current session. The system invalidates the session and redirects the user to the login screen. | Iteration 1 | Done
3 | Reset Password | Authentication & Account | All roles | Nhi | Simple | Allow users to request a password reset by providing their registered account information. The system verifies the request and provides a secure password reset process. | Iteration 1 | Done
4 | Change Password | Authentication & Account | All roles | Nhi | Simple | Allow authenticated users to change their password by providing their current password and a valid new password. The system validates the input and securely updates the password. | Iteration 1 | Done
5 | View User List | User Management & Authorization | Admin | Nhi | Simple | Allow administrators to view a paginated list of user accounts, including key account information, status, assigned roles, and department. The list supports searching, filtering, and opening user details. | Iteration 2 | Done
6 | View User Details | User Management & Authorization | Admin | Nhi | Simple | Allow administrators to view a selected user's account details, including profile information, department, assigned roles, permissions, account status, and relevant account metadata. | Iteration 2 | Done
7 | Add User | User Management & Authorization | Admin | Nhi | Medium | Allow administrators to create a user account by entering the required profile and organizational information. The system validates the input and creates the account with the configured default settings. | Iteration 2 | Done
8 | Edit User | User Management & Authorization | Admin | Nhi | Medium | Allow administrators to update an existing user's profile and account information. The system validates the changes and saves the updated information. | Iteration 2 | Done
9 | Assign Role, Scope & Ownership | User Management & Authorization | Admin | Nhi | Medium | Allow administrators to assign or update a user's roles, access scope, and ownership responsibilities. The system applies the assignments to determine the user's authorized access to system resources. | Iteration 2 | Done
10 | View Users by Department | User Management & Authorization | Admin | Nhi | Complex | Allow administrators to view and filter user accounts by department. The system displays the users belonging to the selected department and their relevant account information. | Iteration 2 | Done
11 | Import Users from Excel | User Management & Authorization | Admin | Nhi | Simple | Allow administrators to upload an Excel file containing multiple user records. The system validates the file structure and required fields, processes valid records, and reports records that cannot be imported. | Iteration 2 | Done
12 | Create Risk Assessment | Risk Assessment | Security Officer | Dương | Medium | Allow Security Officers to create a risk assessment for an active asset or business service by recording its title, description, assessment scope, risk owner, and future review date. The created assessment establishes the initial risk record and provides the basis for subsequent identification of threats and vulnerabilities, evaluation of inherent risk and control effectiveness, assessment of residual and target risk, treatment planning, and risk acceptance. | Iteration 1 | Done
13 | View Risk Register | Risk Assessment | Security Officer | Dương | Simple | Allow authenticated and authorized users to view, search, filter, and paginate the risk register within their assigned access scope. The register displays risk records with key information including risk ratings, associated assets, risk owners, treatment-plan summaries, review dates, and counts of linked incidents. | Iteration 1 | Done
14 | View Risk Detail | Risk Assessment | Security Officer | Dương | Simple | Allow authorized users to view the detailed information of a selected risk within their access scope, including its scope and context, related assets, threats, vulnerabilities, inherent and residual risk assessments, control effectiveness, target risk, treatment plans, owner, status, review date, and linked controls and incidents. | Iteration 1 | Done
15 | Identify Threat | Risk Assessment | Security Officer | Dương | Medium | Allow Security Officers to identify and document a potential threat associated with a risk record by recording its name and description and linking it to one or more existing vulnerabilities belonging to that risk. The threat becomes part of the risk context used by subsequent risk assessments. | Iteration 1 | Done
16 | Identify Vulnerability | Risk Assessment | Security Officer | Dương | Medium | Allow Security Officers to identify and document a vulnerability associated with a risk linked to an asset or business service. The system records the vulnerability name and description and links it to applicable security controls. The vulnerability becomes part of the risk context and may be associated with threats and considered in subsequent risk assessments. | Iteration 1 | Done
17 | Assess Inherent Risk | Risk Assessment | Security Officer | Dương | Medium | Allow Security Officers to assess the inherent risk of a risk associated with an asset or business service after the required threat and vulnerability context has been established. The assessment records likelihood, potential impact, and an assessment reason, then calculates the inherent risk score and rating before considering security controls. | Iteration 1 | Done
18 | Assess Control Effectiveness | Risk Assessment | Security Officer, Control Owner | Dương | Medium | Allow Security Officers and assigned Control Owners to assess the effectiveness of an applicable security control using its current implementation status and available active evidence. The assessment records the test method, result, effectiveness score, and notes for use in residual risk evaluation. | Iteration 1 | Done
19 | Assess Residual Risk | Risk Assessment | Risk Owner | Dương | Medium | Allow the assigned Risk Owner to assess residual risk after considering the current effectiveness and supporting evidence of related security controls. The system records residual likelihood, impact, score, rating, target risk, risk appetite, risk tolerance, and assessment rationale, and indicates whether the residual risk falls within the defined appetite and tolerance. | Iteration 1 | Done
20 | Define Target Risk | Risk Assessment | Risk Owner | Dương | Medium | Allow the assigned Risk Owner to define the target risk level for a selected draft or active treatment plan based on the current residual risk, risk appetite, and risk tolerance. The system ensures that the target risk does not exceed the current residual risk and records the target-risk rationale for future treatment evaluation. | Iteration 1 | Done
21 | Update Risk Treatment Plan | Risk Assessment | Security Officer, Risk Owner | Dương | Medium | Allow Security Officers and the assigned Risk Owner to update an existing risk treatment plan, including its treatment strategy, plan owner, actions, action owners, related controls, target date, and status. The system validates allowed workflow transitions, derives progress from action statuses, and records the changes for ongoing monitoring. | Iteration 1 | Done
22 | Create Risk Treatment Plan | Risk Assessment | Security Officer, Risk Owner | Dương | Medium | Allow Security Officers and the assigned Risk Owner to create a treatment plan for an eligible risk. The plan records the treatment strategy, plan owner, target completion date, treatment actions and their responsible users, related controls, and intended target risk. The system validates the risk context and creates a target-risk assessment associated with the plan. | Iteration 1 | Done
23 | Accept, Review and Reassess Risk | Risk Assessment | Risk Owner, Authorized Approver | Dương | Medium | Allow the assigned Risk Owner to reassess the residual risk, select an eligible treatment plan, and submit a risk acceptance request when acceptance is appropriate. The system creates a new residual assessment, records the acceptance request and validity period, and allows an eligible Security Officer or Executive to approve or reject it. For an accepted risk, the Risk Owner may later open a review to reassess the risk context. | Iteration 1 | Done
24 | Create Policy Draft | Policy Management | Security Officer | Khoa | Medium | Allow Security Officers to create a draft information security policy by entering its title, content, purpose, and other required policy information. The system saves the draft for further editing and review. | Iteration 1 | Done
25 | View List Policy Draft | Policy Management | Security Officer | Khoa | Simple | Allow Security Officers to view a list of policy drafts with key information such as title, status, creator, and last updated time. The list supports searching, filtering, and opening a selected draft. | Iteration 1 | Done
26 | Edit Policy Draft | Policy Management | Security Officer | Khoa | Medium | Allow Security Officers to edit an existing policy draft, including its title, content, and other editable policy information. The system saves the changes while retaining the draft's workflow status. | Iteration 1 | Done
27 | Define Policy Applicability | Policy Management | Security Officer | Khoa | Medium | Allow Security Officers to define the departments, roles, user groups, or organizational scope to which a policy applies. The system records the applicability rationale and reference basis before the policy is submitted for review. | Iteration 1 | Done
28 | Submit Policy for Review | Policy Management | Security Officer | Khoa | Medium | Allow Security Officers to submit a completed policy draft for administrative review. The system records the submission and updates the policy workflow status so that an administrator can review it. | Iteration 1 | Done
29 | View Policy Draft | Policy Management | Admin | Khoa | Simple | Allow administrators to view a submitted policy draft, including its content, applicability, author, submission information, and current review status. | Iteration 1 | Done
30 | Review Policy | Policy Management | Admin | Khoa | Medium | Allow administrators to review a submitted policy draft for completeness, consistency, and compliance with the organization's policy requirements. The system provides the information needed to approve the draft, request revisions, or reject it. | Iteration 1 | Done
31 | Publish Policy Version | Policy Management | Admin, System | Khoa | Medium | Allow administrators to publish an approved policy as an official version. The system records the version and publication information and makes the published policy available to its intended audience. | Iteration 1 | Done
32 | Request Policy Revision | Policy Management | Admin | Khoa | Medium | Allow administrators to return a policy draft to the Security Officer for revision by recording the required changes and review comments. The system updates the workflow status and makes the feedback available to the responsible author. | Iteration 1 | Done
33 | Approve Policy for Publication | Policy Management | Admin | Khoa | Medium | Allow administrators to approve a reviewed policy draft for publication. The system records the approval decision and makes the policy eligible for publication as an official version. | Iteration 1 | Done
34 | Reject Policy | Policy Management | Admin | Khoa | Medium | Allow administrators to reject a policy draft that does not satisfy the required criteria. The system records the rejection decision and its reason, and updates the policy workflow status. | Iteration 1 | Done
35 | View Published Policy | Policy Management | Security Officer, Employee | Khoa | Simple | Allow Security Officers and Employees to view the content and details of an official published policy that is available to them according to its applicability and access permissions. | Iteration 2 | Done
36 | Acknowledge Policy Reading | Policy Management | Employee | Khoa | Simple | Allow Employees to acknowledge that they have read and understood a published policy. The system records the employee, policy version, and acknowledgement time for compliance tracking. | Iteration 2 | Done
37 | View Policy Version History | Policy Management | Security Officer, Admin | Khoa | Simple | Allow authorized Security Officers and administrators to view the version history of a policy, including version identifiers, publication dates, and relevant change information, to support traceability and audit. | Iteration 2 | Done
38 | Send In-System Notification | Notification & System Logs | Admin | Nhi | Medium | Allow administrators to send in-system notifications to selected users or user groups. The system records the notification content and recipients and makes the notification available through the application. | Iteration 2 | Done
39 | Send Email Notification | Notification & System Logs | Admin | Nhi | Simple | Allow administrators to send email notifications to selected recipients. The system records the notification details and delivery status when available. | Iteration 2 | Done
40 | Configure Personal Notification Channel | Notification & System Logs | All roles | Nhi | Medium | Allow users to configure their preferred notification channels using the options supported by the system. The system saves the preferences and applies them to eligible notifications. | Iteration 2 | Done
41 | View User Activity Audit Log | Notification & System Logs | Admin | Nhi | Medium | Allow administrators to view audit records of user activities, including the actor, action, affected resource, timestamp, and outcome, to support monitoring and accountability. | Iteration 2 | Done
42 | Search Logs with Advanced Filters | Notification & System Logs | Admin, Security Officer | Nhi | Medium | Allow administrators and Security Officers to search and filter available system logs using criteria such as time range, event type, source, actor, and processing status, subject to their permissions. | Iteration 2 | Done
43 | Export Investigation Logs | Notification & System Logs | Admin | Nhi | Medium | Allow authorized administrators and Security Officers to export selected investigation logs for further analysis or evidence review. The system applies the selected filters and generates a file containing the matching records. | Iteration 2 | Done
44 | View System Configuration Change History | Notification & System Logs | Admin | Nhi | Medium | Allow administrators to view the history of system configuration changes, including the affected setting, actor, timestamp, and recorded change details, to support traceability. | Iteration 2 | Done
45 | View Asset List | Asset Management | Security Officer, Asset Owner | Dương | Simple | Allow Security Officers and users assigned as Asset Owners to view a paginated list of IT assets within their authorized ownership scope. The list displays key information including asset code, name, type, owner, criticality, data classification, business service, and status. | Iteration 1 | Done
46 | View Asset Detail | Asset Management | Security Officer, Asset Owner | Dương | Simple | Allow Security Officers and users assigned as Asset Owners to view detailed information about an IT asset within their authorized scope, including ownership, business service, criticality, data classification, dependencies, linked event sources, related risks, controls, and incidents. | Iteration 1 | Done
47 | Create Asset | Asset Management | Security Officer | Dương | Medium | Allow Security Officers to create an IT asset record by entering its name and asset type, with optional description, owner, dependencies, and linked event sources. The system validates the information, generates an asset code, and saves the asset for ongoing management. | Iteration 1 | Done
48 | Edit Asset | Asset Management | Security Officer | Dương | Medium | Allow Security Officers to update an existing non-archived IT asset’s name, asset type, and description. The system validates the information and saves the changes while preserving other asset attributes. | Iteration 1 | Done
49 | Archive Asset | Asset Management | Security Officer | Dương | Medium | Allow Security Officers to archive an IT asset that is no longer in use, provided no active assets depend on it. The system marks the asset as archived, records the reason, acting user, and timestamp, and preserves its record and relationships for audit and review. | Iteration 1 | Done
50 | Assign Asset Owner | Asset Management | Security Officer | Dương | Medium | Allow Security Officers to assign, change, or remove the responsible owner of a non-archived IT asset. The system validates that a newly assigned owner is an active user and saves the ownership assignment to establish accountability for the asset. | Iteration 1 | Done
51 | Classify Asset Criticality & Data Classification | Asset Management | Security Officer | Dương | Medium | Allow Security Officers to classify a non-archived IT asset by assessing confidentiality, integrity, availability, and business impacts and selecting its data sensitivity classification. The system calculates asset criticality and records the classifications, supporting rationale, assessor, and assessment date for asset management and subsequent risk and incident review. | Iteration 1 | Done
52 | Link Asset to Business Service, Dependency and Event Source | Asset Management | Security Officer | Dương | Medium | Allow Security Officers to link or unlink an active IT asset to a business service, dependent assets, and configured event sources. The system validates the relationships, prevents self-dependencies and dependency cycles, and saves the links to support contextual review during risk assessment and incident investigation. | Iteration 1 | Done
53 | Create Incident from Confirmed Alert / Finding | Incident Management | Security Officer | Khoa | Medium | Allow Security Officers to create a security incident from a confirmed alert or security finding. The system records the incident details and links the originating alert or finding for traceability. | Iteration 2 | Done
54 | Create Incident Manually | Incident Management | Security Officer | Khoa | Medium | Allow Security Officers to manually create a security incident when no existing alert or finding is available. The system records the reported details and creates an incident for investigation and response. | Iteration 2 | Done
55 | View Incident List | Incident Management | Security Officer, Executive | Khoa | Simple | Allow Security Officers and authorized Executives to view a list of security incidents within their access scope. The list displays key incident information and supports locating and opening a selected incident. | Iteration 2 | Done
56 | View Incident Detail | Incident Management | Security Officer, Executive | Khoa | Simple | Allow Security Officers and authorized Executives to view an incident's details, including its description, severity, status, affected assets, assigned handler, response actions, and handling history. | Iteration 2 | Done
57 | Classify Incident Severity | Incident Management | Security Officer | Khoa | Medium | Allow Security Officers to classify an incident's severity based on the observed circumstances and potential business impact. The system records the severity to support prioritization and response. | Iteration 3 | Done
58 | Assign Incident Handler | Incident Management | Security Officer | Khoa | Medium | Allow Security Officers to assign or change the handler responsible for investigating and managing an incident. The system records the assignment for accountability and follow-up. | Iteration 3 | Done
59 | Record Containment Actions | Incident Management | Security Officer | Khoa | Medium | Allow Security Officers to record containment actions taken to limit the incident's spread or impact. The system saves the actions and their relevant details in the incident response history. | Iteration 3 | Done
60 | Record Eradication Actions | Incident Management | Security Officer | Khoa | Medium | Allow Security Officers to record eradication actions taken to remove the incident's root cause, malicious components, or other identified threats. The system preserves the actions in the incident record. | Iteration 3 | Done
61 | Record Recovery Actions | Incident Management | Security Officer | Khoa | Medium | Allow Security Officers to record recovery actions taken to restore affected systems or services to normal operation. The system saves the recovery details and supports tracking the incident's progress. | Iteration 3 | Done
62 | Perform Root Cause Analysis & Lessons Learned | Incident Management | Security Officer | Khoa | Medium | Allow Security Officers to document the identified root cause, lessons learned, and recommended improvements after an incident has been investigated and addressed. The system stores the findings for future prevention and process improvement. | Iteration 3 | Done
63 | Close Incident | Incident Management | Security Officer | Khoa | Medium | Allow Security Officers to close an incident after the required response and recovery activities are completed and the necessary information is recorded. The system updates the incident status and retains its history for audit and review. | Iteration 3 | Done
64 | View Event Source List | Event Ingestion | Admin, Security Officer | Thịnh | Medium | Allow administrators and Security Officers to view a paginated list of configured event sources, including source name, source type, status, and last update time. The list supports access to the details of a selected source. | Iteration 1 | Done
65 | Register Normalized Event Source | Event Ingestion | Admin, Security Officer | Thịnh | Complex | Allow administrators and Security Officers to register a normalized event source by providing its connection details, authentication configuration, supported event families, and ingestion settings. The system validates the configuration and saves the source for event ingestion. | Iteration 1 | Done
66 | View Event Source Detail | Event Ingestion | Admin, Security Officer | Thịnh | Medium | Allow administrators and Security Officers to view an event source's configuration details, including its name, source type, endpoint, supported event families, and ingestion settings. Sensitive credentials are masked from display. | Iteration 1 | Done
67 | Search / Filter Event Source | Event Ingestion | Admin, Security Officer | Thịnh | Simple | Allow administrators and Security Officers to search registered event sources by name and filter them by attributes such as source type and status. The system displays matching sources within the user's authorized scope. | Iteration 1 | Done
68 | Edit Event Source Configuration | Event Ingestion | Admin, Security Officer | Thịnh | Medium | Allow administrators and Security Officers to modify an existing event source's descriptive information, connection settings, credentials, and ingestion parameters. The system validates and saves the updated configuration. | Iteration 1 | Done
69 | Test Event Source Configuration | Event Ingestion | Admin, Security Officer | Thịnh | Medium | Allow administrators and Security Officers to test an event source's connectivity and authentication using its configured settings. The system displays the test outcome and diagnostic information to help users identify configuration problems before registration or update. | Iteration 1 | Done
70 | Enable / Disable Event Source | Event Ingestion | Admin | Thịnh | Medium | Allow administrators to enable or disable an event source without deleting its configuration. The system updates the source status so that ingestion can be paused or resumed according to the supported integration workflow. | Iteration 1 | Done
71 | Import Normalized Events from File | Event Ingestion | Admin, Security Officer | Thịnh | Medium | Allow administrators and Security Officers to upload a file containing normalized security events, such as CSV or JSON. The system validates the file format and required fields, processes valid records, and records the import result. | Iteration 1 | Done
72 | View Event Import Result / Invalid Events | Event Ingestion | Admin, Security Officer | Thịnh | Medium | Allow administrators and Security Officers to view the result of an event import operation, including the number of successfully processed and rejected records and the validation errors associated with invalid events. | Iteration 1 | Done
73 | View Event List | Event Ingestion | Security Officer | Thịnh | Simple | Allow Security Officers to view a centralized, paginated list of ingested security events. The list displays key attributes such as event timestamp, source, event family, user or account, associated asset, and processing status. | Iteration 2 | Done
74 | View Event Detail | Event Ingestion | Security Officer | Thịnh | Simple | Allow Security Officers to inspect a selected security event's metadata and payload, including source information, ingestion details, extracted attributes, entity mappings, and processing status. | Iteration 2 | Done
75 | Search / Filter Events | Event Ingestion | Security Officer | Thịnh | Simple | Allow Security Officers to search and filter ingested security events using criteria such as time range, event family, source, source IP, user account, associated asset, and ingestion status. | Iteration 2 | Done
76 | Review / Correct Event Entity Mapping | Event Ingestion | Security Officer | Thịnh | Complex | Allow Security Officers to review system-generated mappings between security events and internal entities, such as users, accounts, or assets. Authorized users can correct inaccurate mappings, and the system records the updated associations. | Iteration 2 | Done
77 | View Audit Log List | Audit, Security & Reporting | Admin, Security Officer | Thịnh | Medium | Allow administrators to view a list of system audit records covering user actions, configuration changes, and system access activities. The list provides key details for compliance monitoring and accountability. | Iteration 2 | Done
78 | Search / Filter Audit Logs | Audit, Security & Reporting | Admin, Security Officer | Thịnh | Simple | Allow administrators to search and filter audit records using criteria such as actor, action type, affected resource, correlation ID, and time range. The system displays matching records for investigation and review. | Iteration 2 | Done
79 | View Audit Log Detail | Audit, Security & Reporting | Admin, Security Officer | Thịnh | Simple | Allow administrators to view the detailed information of a selected audit record, including the recorded action, actor, affected resource, request context, relevant parameters, timestamp, and outcome when available. | Iteration 2 | Done
80 | View Before / After Changes | Audit, Security & Reporting | Admin, Security Officer | Thịnh | Medium | Allow administrators to compare the recorded state of an entity before and after a change. The system presents the differences in the available entity properties to support auditing and investigation. | Iteration 2 | Done
81 | View Event Data Governance Policy | Audit, Security & Reporting | Admin | Thịnh | Medium | Allow administrators to view the current event data governance and retention policy, including applicable retention periods, archival rules, and data lifecycle settings. | Iteration 2 | Done
82 | Edit Event Data Governance & Retention Policy | Audit, Security & Reporting | Admin | Thịnh | Complex | Allow administrators to configure event data governance settings, including retention periods, archival thresholds, and lifecycle rules. The system validates and saves the settings for application to eligible event data. | Iteration 2 | Done
83 | View Integration API Key List | Audit, Security & Reporting | Admin | Thịnh | Medium | Allow administrators to view the list of integration API keys, including key names, assigned scopes, status, creator, and expiration information. Secret key values are not exposed in the list. | Iteration 3 | Done
84 | View Integration API Key Detail | Audit, Security & Reporting | Admin | Thịnh | Medium | Allow administrators to view the metadata of a selected integration API key, including its creator, permission scopes, status, creation and expiration times, and available usage information. | Iteration 3 | Done
85 | Create Integration API Key | Audit, Security & Reporting | Admin | Thịnh | Medium | Allow administrators to generate an integration API key by specifying its name, authorized scopes, and expiration settings. The system creates the key, records its metadata, and displays the secret securely according to the supported key-creation workflow. | Iteration 3 | Done
86 | Edit API Key Scope & Expiration | Audit, Security & Reporting | Admin | Thịnh | Medium | Allow administrators to edit an existing API key's authorized scopes or expiration date. The system validates and saves the changes and applies the updated access restrictions. | Iteration 3 | Done
87 | Rotate Integration API Key | Audit, Security & Reporting | Admin | Thịnh | Complex | Allow administrators to rotate an integration API key by generating a replacement key and invalidating the previous key according to the rotation workflow. The system records the operation to support integration continuity and auditing. | Iteration 3 | Done
88 | Revoke Integration API Key | Audit, Security & Reporting | Admin | Thịnh | Medium | Allow administrators to revoke an integration API key so that it can no longer be used for authentication. The system updates the key status and records the revocation for audit purposes. | Iteration 3 | Done
89 | Search / Filter Integration API Keys | Audit, Security & Reporting | Admin | Thịnh | Medium | Allow administrators to search and filter integration API keys by name, creator, status, expiration period, or assigned scopes. The system displays matching keys without exposing secret values. | Iteration 3 | Done
90 | View Security / Risk / Incident Dashboard | Audit, Security & Reporting | Security Officer, Executive | Thịnh | Complex | Allow Security Officers and authorized Executives to view a dashboard summarizing the organization's security posture. The dashboard presents available security indicators, risk metrics, incident statistics, and recent AI-generated alerts within the user's access scope. | Iteration 3 | Done
91 | Export Risk / Incident / Security Report | Audit, Security & Reporting | Security Officer, Executive | Thịnh | Complex | Allow Security Officers and authorized Executives to generate and export risk, incident, and security reports for a selected period using available filters. The system compiles the matching data into a supported format, such as PDF or Excel. | Iteration 3 | Done
92 | Report Export Revoked | Audit, Security & Reporting | Security Officer, Executive | Thịnh | Medium | The language entered is not supported at this time. | Iteration 3 | Done
93 | Run Anomaly Detection | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Allow Security Officers to run anomaly detection on eligible normalized security events using the configured pre-trained AI model and detection settings. The system evaluates the events and produces anomaly scores or candidate alerts without training or fine-tuning the model. | Iteration 1 | Done
94 | Generate Anomaly Score | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Allow Security Officers to view anomaly scores generated by the configured AI model for processed security events. The system displays the score and associated event context to support security analysis. | Iteration 1 | Done
95 | Generate Anomaly Alert | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Allow the system to generate an anomaly alert when an event's anomaly score or detection result satisfies the configured alerting criteria. The alert records the relevant event, score, model version, and detection context for analyst review. | Iteration 1 | Done
96 | View Anomaly Score | AI Anomaly Detection & Alerts | Security Officer | Hoài | Simple | Allow Security Officers to view the anomaly score associated with a selected event or alert, together with the applicable scoring context and configured detection criteria, to support interpretation of the model's output. | Iteration 1 | Done
97 | View Features Contributing to Anomaly | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Allow Security Officers to inspect the event attributes or features that contributed to an anomaly detection result, where supported by the configured model and explanation method. The system presents the available contributing factors for analyst review. | Iteration 1 | Done
98 | View XAI Explanation | AI Anomaly Detection & Alerts | Security Officer | Hoài | Simple | Allow Security Officers to view an explainable AI (XAI) explanation for a selected anomaly result. The system presents the available reasons or contributing factors behind the model's output to support human interpretation. | Iteration 1 | Done
99 | Configure Detection Threshold | AI Anomaly Detection & Alerts | Security Officer, Executive | Hoài | Simple | Allow authorized Security Officers and Executives to configure the detection thresholds used to determine which anomaly scores qualify for alerting. The system validates and saves the thresholds and applies them to subsequent detection results. | Iteration 1 | Done
100 | View Model Version & Evaluation Metrics | AI Anomaly Detection & Alerts | Security Officer | Hoài | Medium | Allow Security Officers to view the configured AI model's name, version, status, and available evaluation metrics. The system presents model metadata to support traceability and interpretation of detection results. | Iteration 1 | Done
101 | Set Custom Alert Threshold | AI Anomaly Detection & Alerts | Security Officer | Hoài | Simple | Allow Security Officers to set a custom alert threshold for a specific asset. The system validates and saves the asset-specific setting and uses it when evaluating eligible events associated with that asset. | Iteration 1 | Done
102 | View Anomaly Alert List | Alert Triage & Analyst Feedback | Security Officer | Hoài | Simple | Allow Security Officers to view a centralized list of AI-generated anomaly alerts, including alert time, associated event or asset, anomaly score, model version, and triage status. The list supports locating alerts for investigation. | Iteration 2 | Done
103 | View Alert Detail | Alert Triage & Analyst Feedback | Security Officer | Hoài | Medium | Allow Security Officers to view the details of a selected anomaly alert, including its triggering event, anomaly score, detection time, associated asset, model version, available explanation, and triage history. | Iteration 2 | Done
104 | Search / Filter Alerts | Alert Triage & Analyst Feedback | Security Officer | Hoài | Simple | Allow Security Officers to search and filter anomaly alerts by criteria such as time range, anomaly score, asset, alert status, and model version. The system displays matching alerts for review. | Iteration 2 | Done
105 | Start Analyst Triage | Alert Triage & Analyst Feedback | Security Officer | Hoài | Simple | Allow Security Officers to begin triage of a selected alert by reviewing its event context, anomaly score, available explanation, and related information. The system records the triage status and assigned analyst where supported. | Iteration 2 | Done
106 | Confirm Alert as True Positive | Alert Triage & Analyst Feedback | Security Officer | Hoài | Simple | Allow Security Officers to confirm that an alert represents a genuine security concern based on the available evidence. The system records the true-positive decision, analyst, timestamp, and feedback details. | Iteration 2 | Done
107 | Dismiss Alert as False Positive | Alert Triage & Analyst Feedback | Security Officer | Hoài | Simple | Allow Security Officers to dismiss an alert as a false positive when the evidence indicates that it does not represent a genuine security concern. The system records the decision, analyst, timestamp, and reason. | Iteration 2 | Done
108 | Mark Alert as Need Further Investigation | Alert Triage & Analyst Feedback | Security Officer | Hoài | Simple | Allow Security Officers to mark an alert as requiring further investigation when the available evidence is insufficient for a final decision. The system records the triage status and preserves the alert for follow-up. | Iteration 2 | Done
109 | Record Feedback Reason, Analyst, Time and Model Version | Alert Triage & Analyst Feedback | Security Officer | Hoài | Simple | Allow Security Officers to record the reason for an alert feedback decision together with the responsible analyst, feedback time, and associated AI model version. The system stores the feedback for traceability and subsequent model evaluation. | Iteration 2 | Done
110 | Link Incident to Asset | Incident → Control Weakness → Risk Reassessment | Security Officer | Hoài | Simple | Allow Security Officers to link a security incident to one or more affected IT assets. The system records the relationships to support impact analysis, asset tracking, and subsequent risk reassessment. | Iteration 3 | Done
111 | Link Incident to Control | Incident → Control Weakness → Risk Reassessment | Security Officer | Hoài | Simple | Allow Security Officers to associate a security incident with relevant security controls. The system records the relationships to help evaluate control performance and identify potential control weaknesses. | Iteration 3 | Done
112 | Link Incident to Existing Risk | Incident → Control Weakness → Risk Reassessment | Security Officer | Hoài | Simple | Allow Security Officers to link a security incident to an existing risk assessment. The system records the relationship to provide incident context for risk review and reassessment. | Iteration 3 | Done
113 | Record Control Weakness from Incident | Incident → Control Weakness → Risk Reassessment | Security Officer | Hoài | Simple | Allow Security Officers to document a control weakness identified during incident investigation. The system records the affected control, supporting evidence, and related incident for follow-up and risk reassessment. | Iteration 3 | Done
114 | Create Risk Reassessment Request | Incident → Control Weakness → Risk Reassessment | Security Officer | Hoài | Simple | Allow Security Officers to create a risk reassessment request based on an incident, identified control weakness, or other relevant findings. The system records the reason, related risk, supporting information, and request status for Risk Owner review. | Iteration 3 | Done
115 | Review Risk Reassessment Request | Incident → Control Weakness → Risk Reassessment | Risk Owner | Hoài | Simple | Allow Risk Owners to review a submitted risk reassessment request, including its rationale, linked incident, identified control weaknesses, and supporting evidence. The Risk Owner records the review decision and any required follow-up. | Iteration 3 | Done
116 | Reassess Residual Risk | Incident → Control Weakness → Risk Reassessment | Risk Owner, Security Officer | Hoài | Medium | Allow the assigned Risk Owner or authorized Security Officer to reassess the residual likelihood, residual impact, and residual risk level based on an approved incident-driven reassessment request, incident findings, and recorded control weaknesses. The system records the revised assessment, assessor, rationale, and assessment time. | Iteration 3 | Done
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple | <=7 fields |  |  | <=3 transactions
| medium | <=15 fields |  |  | <= 7 transactions
| complex | >15 fields |  |  | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 |  |  | Medium |  |  |  | Open
2 |  |  | Medium |  |  |  | Open
3 |  |  | Medium |  |  |  | Open
4 |  |  | Medium |  |  |  | Open
5 |  |  | Medium |  |  |  | Open
6 |  |  | Medium |  |  |  | Open
7 |  |  | Medium |  |  |  | Open

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open